## Product Backlog
Product Backlog ID | Priority | User Story ID | User Story Name | Scrum Team Assigned | Risk | Complexity | Type | Completeness Criteria | Comments
1 | high | ecommSystem001 | login user | Ankita | high | high | functional | 15 hrs
2 | high | ecommSystem002 | user dashboard |  | low | low | functional | 15 hrs
3 | high | ecommSystem003 | register user |  | low | low | functional | 15 hrs
4 | high | ecommSystem004 | product management |  | high | high | functional | 20 hrs
5 | low | ecommSystem005 | search functionality |  | low | low | functional | 10 hrs
6 | high | ecommSystem006 | shipping and tracking |  | high | high | functional | 22 hrs
7 | high | ecommSystem007 | customer reviews |  | low | low | non-functional | 8 hrs
8 | high | ecommSystem008 | security and compliance |  | high | high | functional | 25 hrs
9 | high | ecommSystem009 | payment |  | high | high | functional | 14 hrs
10 | low | ecommSystem010 | wishlist |  | low | low | functional | 10 hrs

## Sprint Backlog 1
Product Backlog id | User Story ID | User Story Step number | Task Description | Assigned To | Assigned Date | Estimate time
1 | ecommSystem001 | 1 | enter the valid user name password | Ritika | 2024-02-20 | 3 hrs
|  | 2 | check username and password from database, if it is valid user is logged in | Kalai | 2024-02-20 | 4 hrs
|  | 3 | if user idel for 10 mts then logout automatically | Jyothi | 2024-02-20 | 4 hrs
|  | 4 | if user enters wrong username or password, throw some exception message | Vishnu | 2024-02-20 | 4 hrs
2 | ecommSystem002 | 1 | homepage | Kalai | 2024-02-21 | 3 hrs
|  | 2 | product categories | Jyothi | 2024-02-21 | 3 hrs
|  | 3 | account | Vishnu | 2024-02-21 | 3 hrs
|  | 4 | cart | Ritika | 2024-02-21 | 3 hrs
|  | 5 | customer service | Vishnu | 2024-02-21 | 3 hrs
3 | ecommSystem003 | 1 | create a necessary class for user and add the required fields | Kalai | 2024-02-22 | 8 hrs
|  | 2 | take the input from user, and store in database, if no user exists, else throw user already execption | Jyothi | 2024-02-22 | 7 hrs

## Sprint backlog 2
Product Backlog id | User Story ID | User Story Step number | Task Description | Assigned To | Assigned Date | Estimate time
4 | ecommSystem004 | 1 | List of products | Ritika | 2024-02-24 | 7 hrs
|  | 2 | Categorize the products | Kalai | 2024-02-24 | 6 hrs
|  | 3 | Product recommendations | Jyothi | 2024-02-24 | 7 hrs
5 | ecommSystem005 | 1 | Sorting | Kalai | 2024-02-25 | 3 hrs
|  | 2 | Filtering | Jyothi | 2024-02-25 | 2 hrs
|  | 3 | Search history | Vishnu | 2024-02-25 | 2 hrs
|  | 4 | Saved searches | Ritika | 2024-02-25 | 3 hrs
6 | ecommSystem006 | 1 | Estimated delivery date | Kalai | 2024-02-26 | 4 hrs
|  | 2 | Online tracking | Jyothi | 2024-02-26 | 4 hrs
|  | 3 | Delivery notification | Vishnu | 2024-02-26 | 5 hrs
|  | 4 | Shipping options | Ritika | 2024-02-26 | 5 hrs
|  | 5 | Return management | Kalai | 2024-02-26 | 4 hrs